## Sheet1
Cost Estimate
Project name: Walk Tracker
WBS Categories | Team Cost($) | Total time per week(hrs) | Cost per week($) | Total cost(for six sprints)($)
1.Initiating | 380 | 8 | 3040 | 36480
2.Planning and designing | 420 | 12 | 5040 | 60480
3.Designing | 450 | 13 | 5850 | 70200
2.1. Wireframe the UI | - | 3 | - | -
2.2 Combination of design | - | 4 | - | -
2.3.Design Evaluation | - | 3 | - | -
2.4.Claiming and Finalizing contract | - | 3 | - | -
3. Execution | 480 | 10 | 4800 | 57600
3.1. Developing the application | - | 4 | - | -
3.2.PWA implementation | - | 3 | - | -
3.3.Mobile execution | - | 3 | - | -
4.Monitoring and Controlling | 370 | 9 | 3330 | 39960
5.Closing | 395 | 8 | 3160 | 37920
Total |  |  |  | 302640
|  | Designation | $/hour
|  | Project Manager | 80
|  | DB Administrator | 75
|  | Team Lead | 72
|  | Full stack Developer | 68
|  | Full stack Developer | 68
|  | Full stack Developer | 68