## Sheet1
Project name: Walk Tracker
WBS Categories | Team Cost($) | Total time per week(hrs) | Cost per week($) | Total cost(for three sprints)($)
1.Initiating | 380 | 8 | 3040 | 18240
2.Planning and designing | 420 | 12 | 5850 | 35100
3.Designing | 450 | 13 | 5850
2.1. Wireframe the UI |  | 3 | - | -
2.2 Combination of design |  | 4 | - | -
2.3.Design Evaluation |  | 3 | - | -
2.4.Claiming and Finalizing contract |  | 3 | - | -
3. Execution | 480 | 10 | 4800 | 28800
3.1. Developing the application |  | 4 | - | -
3.2.PWA implementation |  | 3 | - | -
3.3.Mobile execution |  | 3 | - | -
4.Monitoring and Controlling | 370 | 9 | 3330 | 19980
5.Closing | 395 | 8 | 3160 | 18960
Total