## Sheet1
Cost Estimate
Project name: Walk Tracker
WBS Categories | Team Cost($) | Total time per week(hrs) | Cost per week($) | Total estimated cost(for six sprints)($)
1.Initiating | 380 | 14 | 5320 | 63840
2.Planning | 420 | 19 | 7980 | 95760
3.Designing | 450 | 21.5 | 9675 | 116100
2.1. Wireframe the UI | - | 8 | - | -
2.2 Combination of design | - | 6 | - | -
2.3.Design Evaluation | - | 5 | - | -
2.4.Claiming and Finalizing contract | - | 2.5 |  | -
4. Execution | 480 | 23 | 11040 | 132480
3.1. Developing the application | - | 8 | - | -
3.2.PWA implementation | - | 7 | - | -
3.3.Mobile execution | - | 8 | - | -
4.Monitoring and Controlling | 370 | 14 | 5180 | 62160
5.Closing | 395 | 12 | 4740 | 56880
Total |  |  |  | 527220
|  | Designation | $/hour
|  | Project Manager | 80
|  | DB Administrator | 75
|  | Team Lead | 72
|  | Full stack Developer | 68
|  | Full stack Developer | 68
|  | Full stack Developer | 68